## How to use
TQX Content Machine: Build Checklist
GATC + QUBE · Editor is human for now · Full detail in AGENTS-AND-SKILLS-PLAN.md
Tab | What it's for
Dashboard | Overall progress. Fills in automatically. Don't edit.
Skills | All 34 skills. Update the yellow Status column as you work. Add notes in the Notes column.
Agents | All 11 agents. "Skills done" and "Ready?" fill in automatically from the Skills tab. Update the yellow Status column when you build one.
Agent x Skill | Which agent loads which skill (✓). Reference only.
Setup & Inputs | Non-skill tasks: tools, accounts, and the raw material Mark needs to collect. Update the yellow Status column.
Yellow cells | The only cells you edit. Pick from the dropdown.
Skill status | Not started → In progress → Drafted → Reviewed → Done
Agent status | Not started → Building → Testing → Live
START HERE | terminology and gold-standard-scripts save the most fixing time. Do them first.
Who builds | Mark = only Mark knows it · Pipeline = built from the link database / recordings · Claude drafts, Mark corrects · Already exists
Phase | 1 Foundation · 2 Study pipeline · 3 Analytics · 4 Feedback · 5 Competitors · 6 Production · 7 Automate · 8 Later
Tip | For every rule you write in a skill, include a bad line and a fixed line. Claude follows examples far more reliably than rules.

## Dashboard
Progress
Fills in automatically from the other tabs.
Skills by who builds | Total | Done | % done
Mark
Pipeline
Claude drafts, Mark corrects
Already exists
All skills
Skills by phase | Total | Done | % done
1 Foundation
2 Study pipeline
3 Analytics
4 Feedback
5 Competitors
6 Production
Agents | Count
Total agents
All skills ready (can build now)
Building
Testing
Live
Setup & inputs | Count
Total tasks
Done
Mark's tasks still open

## Skills
# | Skill | Group | Who builds | Phase | Priority | What goes in it | What Claude gets wrong without it | Used by (agents) | # agents | Status | Notes
1 | audience-profile | A. Who we're talking to | Mark | 1 |  | Each persona: trading experience, what they already know and believe, pains, goals, objections, what they've been burned by (signal groups, bots, courses), awareness stage (never heard of AI trading → ready to join GATC). | Pitches at the wrong level: explains what they know, skips what they don't, writes for a generic "trader". | Director, Scriptwriter, Competitor scout |  | Not started
2 | audience-language | A. Who we're talking to | Pipeline | 2 |  | The exact phrases the audience uses, taken from comments, DMs, Reddit and competitors' comment sections, grouped by pain point. | Writes in marketer language instead of the words the audience uses. | Scriptwriter |  | Not started
3 | product-truth-gatc | B. What we're talking about | Mark | 1 |  | What GATC is, how it works step by step, what's live today vs roadmap, real numbers with source and date, what it is NOT. Seed from the existing tqx-gatc-workflow skill. | Invents features, describes the mechanics wrong, uses outdated numbers. | Scriptwriter, Script critic, Production, B-roll |  | Not started
4 | product-truth-qube | B. What we're talking about | Mark | 1 |  | Same structure as product-truth-gatc, for QUBE. | Invents features, describes the mechanics wrong, uses outdated numbers. | Scriptwriter, Script critic, Production, B-roll |  | Not started
5 | terminology | B. What we're talking about | Mark | 1 | START HERE | Glossary table: approved term, definition, never-say synonyms, capitalisation, explain-or-assume per audience, internal-only flag, and a correct-in-a-sentence example for each. | Synonyms drifting (bot / algo / model / agent), wrong definitions, internal jargon leaking into scripts. | Scriptwriter, Script critic, B-roll |  | Not started
6 | trading-fundamentals | B. What we're talking about | Claude drafts, Mark corrects | 1 |  | Correct meanings at the right depth (drawdown, win rate, sim vs live, backtest vs forward test, leverage, etc.), common misconceptions, and how WE explain each. | Statements that are slightly wrong, which experienced traders spot instantly. | Scriptwriter, Script critic |  | Not started
7 | claims-and-proof | B. What we're talking about | Mark | 1 |  | Every approved claim, paired with its proof (screenshot, leaderboard, result) and its allowed wording. | Unproven "trust me" claims, which kill trust in a sceptical finance audience. | Scriptwriter, B-roll |  | Not started
8 | positioning | B. What we're talking about | Mark | 1 |  | How we differ from signal groups, copy-trading, other AI bots and courses; the enemy we push against; comparisons we never make. | Sounds like every other trading account. | Director, Scriptwriter, Competitor scout |  | Not started
9 | tqx-voice | C. How we sound | Mark | 1 |  | Mark's rewrite. Who's speaking, point of view (I / we / you), attitude, energy, humour level, stance on hype. Built from transcripts of Mark talking naturally. | Falls back to Claude's default polite, explainer voice. | Scriptwriter, Script critic |  | Not started
10 | spoken-sentence-rules | C. How we sound | Claude drafts, Mark corrects | 1 |  | Sentence length range, one idea per sentence, contractions, how sentences may start, rhythm, punctuation for delivery, read-aloud test. Every rule has a bad line and a fixed line. | Essay sentences that read fine on paper but sound wrong when spoken. | Scriptwriter, Script critic |  | Not started
11 | anti-ai-patterns | C. How we sound | Claude drafts, Mark corrects | 1 |  | Banned patterns with fixes: "It's not X, it's Y", lists of three, em dashes, "Here's the thing", "Let's dive in", "game-changer", rhetorical-question chains, colon reveals, hedging, summary endings, motivational filler. | The giveaways that make a script sound AI-written. | Scriptwriter, Script critic |  | Not started
12 | hook-writing | D. How a script is built | Pipeline | 2 |  | From the link database: hook types, formulas, rules for the first 1–3 seconds, how spoken and on-screen text work together. | Generic, slow, or clickbait hooks that don't fit TQX. | Director, Scriptwriter, Retention analyst |  | Not started
13 | story-structures | D. How a script is built | Pipeline | 2 |  | From the link database: named structures with their beats, which goal each fits, seconds per beat at 30/45/60s. | Shapeless middles; payoff in the wrong place. | Scriptwriter, Retention analyst |  | Not started
14 | retention-writing | D. How a script is built | Pipeline | 2 |  | From the link database: open loops, a re-hook every few seconds, pattern breaks, payoff placement. | Viewers leave in the middle. | Scriptwriter, Retention analyst |  | Not started
15 | script-logic | D. How a script is built | Claude drafts, Mark corrects | 1 |  | The reasoning chain: the hook's promise must be paid off; every line answers "so what?" or "how?"; no skipped steps; correct cause and effect; one main idea per video; the explain-it-to-a-friend test. | Scripts that sound fine line by line but don't make sense as a whole. | Director, Scriptwriter, Script critic, Retention analyst |  | Not started
16 | content-formats | D. How a script is built | Mark | 1 |  | Our recurring formats (e.g. GATC leaderboard update, AI-vs-AI, behind the build, myth-bust): template, length, when to use each. | Reinvents the format every time; inconsistent series. | Director, Scriptwriter |  | Not started
17 | cta-and-offer | D. How a script is built | Mark | 1 |  | What we ask for at each goal (follow, comment a keyword, join GATC, try QUBE), exact wording, where it goes. | Missing, random, or wrong-offer CTAs. | Scriptwriter |  | Not started
18 | on-screen-text | D. How a script is built | Claude drafts, Mark corrects | 1 |  | What goes on screen vs what's spoken, caption length, never duplicating the voiceover. Sharpened by link-database lessons. | Scripts with nothing for the screen, or text that fights the voiceover. | Scriptwriter, Production |  | Not started
19 | finance-compliance | E. Guardrails | Mark | 1 |  | No return promises, required disclaimers, sim-vs-live wording, banned phrases ("guaranteed", "passive income", etc.). | Claims that are legally risky or look like a scam. | Director, Scriptwriter, Script critic |  | Not started
20 | gold-standard-scripts | F. Quality | Mark | 1 | START HERE | 10–20 approved scripts annotated line by line with why each line works, plus rejected scripts with why they failed. | Misreads the rules; good examples teach more than rules do. | Director, Scriptwriter |  | Not started
21 | fix-log | F. Quality | Claude drafts, Mark corrects | 1 |  | Every correction Mark makes: original line → fix → reason → which rule it breaks. Repeated fixes get promoted into rules by the Skill updater. | The same mistake gets fixed for weeks instead of once. | Scriptwriter, Script critic, Skill updater |  | Not started
22 | script-qa-checklist | F. Quality | Claude drafts, Mark corrects | 1 |  | The line-by-line review the Script critic runs before any script reaches Mark. | Problems reach Mark instead of being caught first. | Script critic |  | Not started
23 | content-strategy | G. Strategy | Mark | 1 |  | Content pillars, posting mix, what each week should push (GATC vs QUBE), goals per pillar. | Random topics with no plan behind them. | Director |  | Not started
24 | content-scorecard | G. Strategy | Mark | 1 |  | The metrics that define "good" (e.g. 3-second hold, average watch %, shares per 1k views) and the targets for each. | Approvals based on gut feel; no way to tell if the machine is improving. | Director, Analytics |  | Not started
25 | storyboarding | H. Production | Pipeline | 6 |  | From the link database plus storyboards Mark likes: turning lines into shots (framing, angle, movement, duration). | Shot lists that are vague or impossible to film. | Production |  | Not started
26 | filming-setup | H. Production | Mark | 6 |  | Mark's gear, locations, lighting, and how he films. | Plans shots that can't be filmed with the gear available. | Production |  | Not started
27 | broll-sourcing | H. Production | Mark | 6 |  | Every GATC/QUBE screen and account available to capture, and how to capture each (recording settings, crop, what to hide). | Asks for visuals that don't exist or can't be captured. | B-roll |  | Not started
28 | video-breakdown | I. Research | Claude drafts, Mark corrects | 2 |  | The fixed lesson-card format: claims, rules, example hooks, structure, timestamps, source link. | Every video analysed differently, so lessons can't be combined. | Video analyst, Competitor scout |  | Not started
29 | kb-curation | I. Research | Claude drafts, Mark corrects | 2 |  | How to tag, dedupe and score knowledge: strong (several creators) / contested / single-source. | Duplicate or contradictory rules piling up in the knowledge base. | Librarian |  | Not started
30 | remix-for-product | I. Research | Claude drafts, Mark corrects | 5 |  | How to keep a viral video's structure and hook but rebuild it around GATC/QUBE, without copying footage. | Copies competitors too closely, or loses what made the original work. | Competitor scout |  | Not started
31 | skill-creator | I. Research | Already exists | 2 |  | Anthropic's format for writing and structuring a SKILL.md. Already installed. | Badly structured skills that load the wrong detail at the wrong time. | Librarian, Skill updater |  | Done
32 | metrics-definitions | J. Feedback | Claude drafts, Mark corrects | 3 |  | Which numbers to pull from Instagram, what each means, how to compare videos fairly (age of post, reach). | Compares posts unfairly and draws wrong conclusions. | Analytics |  | Not started
33 | retention-diagnosis | J. Feedback | Claude drafts, Mark corrects | 4 |  | How to read a retention graph and turn a drop at a timestamp into a script cause. | Knows where people left but not why. | Retention analyst |  | Not started
34 | skill-updating | J. Feedback | Claude drafts, Mark corrects | 4 |  | Rules for changing a skill: minimum sample size, show a diff, Mark approves, log the change. | Skills drift after one bad video. | Skill updater |  | Not started

## Agent x Skill
Skill | Status | Director | Scriptwriter | Script critic | Production | B-roll | Video analyst | Librarian | Competitor scout | Analytics | Retention analyst | Skill updater
|  | ✓ | ✓ | [5 empty] | ✓
✓
|  |  | ✓ | ✓ | ✓ | ✓
|  |  | ✓ | ✓ | ✓ | ✓
|  |  | ✓ | ✓ |  | ✓
|  |  | ✓ | ✓
|  |  | ✓ |  |  | ✓
|  | ✓ | ✓ | [5 empty] | ✓
|  |  | ✓ | ✓
|  |  | ✓ | ✓
|  |  | ✓ | ✓
|  | ✓ | ✓ | [7 empty] | ✓
|  |  | ✓ | [7 empty] | ✓
|  |  | ✓ | [7 empty] | ✓
|  | ✓ | ✓ | ✓ | [6 empty] | ✓
|  | ✓ | ✓
✓
|  |  | ✓ |  | ✓
|  | ✓ | ✓ | ✓
|  | ✓ | ✓
|  |  | ✓ | ✓ | [7 empty] | ✓
✓
✓
|  | ✓ | [7 empty] | ✓
✓
✓
✓
[7 empty] | ✓ |  | ✓
✓
✓
[8 empty] | ✓ |  |  |  | ✓
✓
✓
✓

## Agents
# | Agent | Loop | Phase | Job | Skills it loads | Skills needed | Skills done | Ready? | Status | Notes
1 | Director | Production | 1 | Sets the weekly content plan and the angle for each video; approves the outline, script and final cut. | content-strategy audience-profile positioning content-formats content-scorecard script-logic hook-writing finance-compliance gold-standard-scripts |  |  |  | Not started
2 | Scriptwriter | Production | 1 | Writes in passes (outline → draft → voice pass) with estimated timestamps per line. | audience-profile audience-language product-truth-gatc product-truth-qube terminology trading-fundamentals claims-and-proof positioning tqx-voice spoken-sentence-rules anti-ai-patterns hook-writing story-structures retention-writing script-logic content-formats cta-and-offer on-screen-text finance-compliance gold-standard-scripts fix-log |  |  |  | Not started
3 | Script critic | Production | 1 | Reviews every script line by line before the Director sees it and sends it back with specific fixes. | script-qa-checklist terminology product-truth-gatc product-truth-qube trading-fundamentals spoken-sentence-rules anti-ai-patterns script-logic tqx-voice finance-compliance fix-log |  |  |  | Not started
4 | Production | Production | 6 | Turns the locked script into a storyboard and shot list. | storyboarding filming-setup on-screen-text product-truth-gatc product-truth-qube |  |  |  | Not started
5 | B-roll | Production | 6 | Lists every screen recording and screenshot needed, with a capture checklist. | broll-sourcing claims-and-proof product-truth-gatc product-truth-qube terminology |  |  |  | Not started
6 | Video analyst | Research | 2 | Downloads, transcribes and grabs frames, then writes one lesson card per video. | video-breakdown |  |  |  | Not started
7 | Librarian | Research | 2 | Combines lesson cards into skills and ranks rules (strong / contested / single-source). | kb-curation skill-creator |  |  |  | Not started
8 | Competitor scout | Research | 5 | Finds top-performing Reels in the niche and writes remix-for-GATC/QUBE briefs. | video-breakdown remix-for-product audience-profile positioning |  |  |  | Not started
9 | Analytics | Feedback | 3 | Pulls metrics for each post and matches them to the video ID and its script. | metrics-definitions content-scorecard |  |  |  | Not started
10 | Retention analyst | Feedback | 4 | Maps each drop-off to a script line and gives the cause. | retention-diagnosis hook-writing story-structures retention-writing script-logic |  |  |  | Not started
11 | Skill updater | Feedback | 4 | Turns patterns in the data and in Mark's fixes into proposed skill changes; Mark approves each one. | skill-updating fix-log skill-creator |  |  |  | Not started

## Setup & Inputs
# | Task | Why | Who | Phase | Link | Status | Notes
1 | Create the content-machine folder and put it in git | Every skill change becomes a diff you can read and roll back | Claude | 1 |  | Not started
2 | Write CLAUDE.md (products, audience summary, scorecard) | Every agent reads it first | Claude drafts, Mark corrects | 1 |  | Not started
3 | Build the automatic script checker | Catches banned phrases, em dashes, non-glossary terms and long sentences every time | Claude | 1 |  | Not started
4 | Collect recordings of Mark talking naturally (voice notes, lives, best videos) | Raw material for tqx-voice | Mark | 1 |  | Not started
5 | Collect 10–20 approved scripts and some rejected ones | Raw material for gold-standard-scripts | Mark | 1 |  | Not started
6 | Build the IG link database, tagged by topic (hooks / storytelling / retention / editing) | Feeds hook-writing, story-structures, retention-writing, storyboarding | Mark | 2 |  | Not started
7 | Decide on yt-dlp for downloading Reels (against Instagram's terms) or manual saving | The transcriber needs the video file | Mark | 2 |  | Not started
8 | Install ffmpeg, whisper-cpp and yt-dlp | Frames + transcripts so Claude can study videos | Claude | 2 |  | Not started
9 | Build the study-video tool (download → transcript → frames → lesson card) | Turns each link into a lesson card | Claude | 2 |  | Not started
10 | Set up video IDs (VID-### folder per video) | Links brief → script → shots → post → metrics | Claude | 3 |  | Not started
11 | Switch Instagram to a Business/Creator account linked to a Facebook Page | Required for the Instagram insights API | Mark | 3 | https://business.facebook.com/ | Not started
12 | Create Meta developer access for Instagram insights | Lets the Analytics agent pull metrics | Mark | 3 | https://developers.facebook.com/apps/ | Not started
13 | Screenshot the retention graph for each post (ongoing) | The API doesn't give the second-by-second curve | Mark | 4 |  | Not started
14 | List the competitor accounts to watch | Input for the Competitor scout | Mark | 5 |  | Not started
15 | Schedule runs: research daily, feedback weekly | Makes the machine run without you starting it | Claude | 7 |  | Not started
16 | Later: add the Editor agent and find where the earlier one lives | Editing is human for now | Mark | 8 |  | Not started